## Volunteer Requirements
Church Field Day — Volunteer Requirements
Activity | Signup Deadline | The Cathedral | New Beginnings | Newport News | Downtown Hampton | Kecoughtan Road | Ingleside Road | Port Norfolk | Downtown Franklin | Total Needed
Food (Servers) | 3 wks out | 12 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 68
Drinks | 3 wks out | 5 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 13
Games (General) | 2 wks out | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12
DJ / Music | 2 wks out | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8
Karaoke | 2 wks out | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8
Basketball | 3 wks out | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 48
Kid Games | 2 wks out | 11 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 19
Parking | 2 wks out | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 12
Site Setup | 2 wks out | 11 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 19
Popcorn Machine | 2 wks out | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8
Pretzels | 2 wks out | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8
GRAND TOTAL |  | 58 | 27 | 23 | 23 | 23 | 23 | 23 | 23 | 223

## Signup Tracker
Church Field Day — Signup Tracker
Site | Activity | Volunteer Name | Phone Number | Email Address | Availability / Shift | Status | Last Updated
The Cathedral
| ← Activity → | Name | Phone | Email | Availability | Status | Last Updated
New Beginnings
| ← Activity → | Name | Phone | Email | Availability | Status | Last Updated
Newport News
| ← Activity → | Name | Phone | Email | Availability | Status | Last Updated
Downtown Hampton
| ← Activity → | Name | Phone | Email | Availability | Status | Last Updated
Kecoughtan Road
| ← Activity → | Name | Phone | Email | Availability | Status | Last Updated
Ingleside Road
| ← Activity → | Name | Phone | Email | Availability | Status | Last Updated
Port Norfolk
| ← Activity → | Name | Phone | Email | Availability | Status | Last Updated
Downtown Franklin
| ← Activity → | Name | Phone | Email | Availability | Status | Last Updated

## Site Summary Dashboard
Church Field Day — Site Summary Dashboard
Site | Food (Servers) | Drinks | Games (General) | DJ / Music | Karaoke | Basketball | Kid Games | Parking | Site Setup | Popcorn Machine | Pretzels | Site Total
The Cathedral | 12 | 5 | 5 | 1 | 1 | 6 | 11 | 4 | 11 | 1 | 1 | 58
New Beginnings | 8 | 2 | 1 | 1 | 1 | 6 | 2 | 2 | 2 | 1 | 1 | 27
Newport News | 8 | 1 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 23
Downtown Hampton | 8 | 1 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 23
Kecoughtan Road | 8 | 1 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 23
Ingleside Road | 8 | 1 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 23
Port Norfolk | 8 | 1 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 23
Downtown Franklin | 8 | 1 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 23
GRAND TOTAL | 68 | 13 | 12 | 8 | 8 | 48 | 19 | 12 | 19 | 8 | 8 | 223

## Event Timeline
Church Field Day — Event Timeline & Checklist
When | Activity | Action Item | Owner | Done?
8 wks out | All | Confirm event date, venue, and site leads | Event Chair
6 wks out | All | Run FieldDay_CreateForms.gs to create all 11 Google Forms | Tech Lead
6 wks out | All | Run setupTriggers() in FieldDay_Confirmation_System.gs | Tech Lead
6 wks out | All | Publish Google Sites page + embed all 11 forms | Tech Lead
5 wks out | All | Announce signups to all 8 sites | Communications
3 wks out | Food | Signup deadline — confirm 12 servers for Cathedral, 8 each other site | Food Chair
3 wks out | Drinks | Signup deadline — confirm counts per site | Drinks Lead
3 wks out | Basketball | Signup deadline — confirm 1 team per site (6 players) | Sports Chair
2 wks out | All other activities | Signup deadline for all remaining activities | Event Chair
2 wks out | All | Review Dashboard tab — follow up on gaps | Event Chair
1 wk out | Site Setup | Confirm tables/chairs/tents count, assign pickup | Setup Lead
1 wk out | Parking | Brief parking volunteers, assign zones | Parking Lead
1 wk out | Food | Assign food items to each site station | Food Chair
3 days out | All | Send final confirmation emails to all volunteers | Event Chair
Day of | Site Setup | Arrive 3 hrs early — tents, tables, chairs | Setup Crew
Day of | Parking | Arrive 1 hr early — briefing and zone assignment | Parking Lead
Day of | Food / Drinks | Arrive 1 hr early — station setup | Food/Drink Leads
Day of | Popcorn/Pretzels | Arrive 45 min early — equipment test | Station Leads
Day of | Kid Games | Arrive 30 min early — area setup and safety check | Kid Games Lead
After event | All | Teardown — tables, chairs, tents back to owners | Setup Crew
After event | All | Thank-you emails sent to all volunteers | Event Chair